## ورقة1
Type | Current Situation / Considerations | Proposed Solution / Benefits | Feasibility Result
Technical | Warnings reach people late or through few channels; phone calls and paper lists; no live picture of affected areas or resource stock. | Web application (HTML/CSS/JavaScript, Leaflet/OpenStreetMap maps, Node.js + PostgreSQL); SMS/email/push alert gateway; weather and seismic data feeds; cloud backup. | ✅ Technically feasible
Operational | Manual assignment of teams, shelters and supplies causes wrong or duplicated deliveries; counting errors waste critical time; staff may resist change. | Live resource inventory and suggested allocation by severity and population; faster alerts; one dashboard for decision makers; less duplication; operator training. | ✅ Operationally feasible
Economic | Cost of software, cloud hosting, alert gateway fees, training, and maintenance (first year $3,000 – $6,200). | Estimated annual savings of $8,000 – $15,000+ from less wasted relief and faster response; open-source tools keep development cost low. | ✅ Cost-effective
Legal | Need to protect citizens' personal data (phone numbers, locations) and restrict who may issue alerts; agreements with mobile operators and data providers. | Data privacy and security policies; role-based access control so only authorized staff issue alerts; data-sharing agreements with weather and relief agencies. | ✅ Legally feasible
Schedule | Working version needed before the next disaster season; records are lost and processes are slow while the manual system remains. | Planned timeline of 90 days (planning 14, analysis 18, design 31, implementation 27 days). | ✅ Achievable timeline

## ورقة2
Cost–Benefit Analysis – Disaster Alert & Resource Allocation System
Category | Description | Estimated Cost | Benefits | Estimated Value (per year)
Software | In-house development, map and mobile-friendly web interface, tool licenses | $1,500 – $3,000 | One central system replaces phone calls and paper lists, reducing errors and delays. | $3,000 saved from fewer errors and delays
Hardware | Cloud server hosting, database and backup storage | $600 – $1,200 | High availability during emergencies and safe data backup. | $1,500 saved from lost records and downtime
Alert Gateway | SMS, email and push notification services, weather/seismic data feeds (annual) | $400 – $900 annually | Warnings reach people in affected areas within minutes. | $4,000 saved from less wasted relief supplies
Training | Onboarding for operators and relief staff, quick guide sessions | $200 – $500 | Correct use of the system and a confident response team. | Higher productivity (≈ $1,000)
Maintenance | Annual updates, bug fixes, security patches and drills | $300 – $600 annually | Continuous stability, security and readiness. | $1,500 saved from avoided outages
Public Safety | Late warnings and misdirected resources under the current manual process | – | Faster response, fewer lives and less property lost, greater public trust. | Intangible but very high value
## Summary
Total Estimated Costs (first year): $3,000 – $6,200
Total Estimated Annual Benefits/Savings: $8,000 – $15,000+
Payback Period: Within 1 year
Conclusion: The Disaster Alert & Resource Allocation System is economically feasible, with clear savings in resources and time and a major gain in public safety.